## Sheet1
TASKSHEET
Team members: |  |  | Project information
Name |  | Student ID | Project title | Build a hotel service managament system
Truong Van Khai |  | 21520274 | Course code | SE104.N23
Ngo Phuc Danh |  | 21521924 | Planned by | Truong Van Khai
Le Ngo Minh Duc |  | 21520195
Le Yen Nhi |  | 21522427
No. | Task title | Date of preparation |  | Taker | Status
|  | Planned start date | Planned completed date
System modelling
1 | Entity relation diagram | 24/4/2023 | 2023-08-05 | Truong Van Khai | Finish
2 | Sequence diagram | 24/4/2023 | 2023-08-05 | Truong Van Khai | Finish
3 | System requirement specification | 24/4/2023 | 2023-08-05 | Ngo Phuc Danh | Finish
4 | System design specification | 24/4/2023 | 2023-08-05 | Ngo Phuc Danh | Finish
5 | State diagram | 24/4/2023 | 2023-08-05 | Le Ngo Minh Duc | Finish
6 | Use case specification | 24/4/2023 | 2023-08-05 | Le Ngo Minh Duc | Finish
7 | Use case diagram | 24/4/2023 | 2023-08-05 | Le Yen Nhi | Finish
8 | Activity diagram | 24/4/2023 | 2023-08-05 | Le Yen Nhi | Finish
9 | Requirement analysis | 24/4/2023 | 2023-08-05 | Whole team | Finish
10 | Class diagram | 24/4/2023 | 2023-08-05 | Truong Van Khai | Finish
11 | Creating guest account | 2023-10-05 | 30/6/2023
12 | Booking room
13 | Request Service
14 | Check the event
15 | Check the room
16 | Guest List
17 | Creating employee account
18 | Creating an event
19 | Booking list
20 | Add room
21 | List room service
22 | Announcements list
23 | Refunds
25 | Room information
26 | Event information
27 | Booking information
28 | Announcements
29 | My task
31 | Announcements
32 | Food menu
33 | Storage